## Walls
Viewer ID | Revit ID | Name | Wall:ID | Walll:Type | Wall:Type | Wall:Level | Wall:Width | Wall:Function | Wall:Structural | Size:Area (ft^2) | Size:Length (ft) | Size:Height (ft) | Construction:Supplier | Construction:Installer | Construction:Status | PJC:Cost ($/LF) | PJC:Total Cost ($) | PJC:Schedule | PJC:Productivity | PJC:Crew Size | PJC:Total Hours | PJC: Crew Days
2849 | 315302 | Basic Wall | A1 | A | Generic - 2" | Level 6 | 2" | Cube | No | 62.173 | 8.799 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 477.3457 | 2018-11-14 10:54 | 3.14 | 1 | 2.8022 | 0.35028
2850 | 315416 | Basic Wall | A2 | A | Generic - 2" | Level 6 | 2" | Cube | No | 58.148 | 8.307 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 450.6548 | 2018-11-14 19:18 | 3.14 | 1 | 2.6455 | 0.33069
2851 | 315534 | Basic Wall | A3 | A | Generic - 2" | Level 6 | 2" | Cube | No | 84.36 | 12.218 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 662.8265 | 2018-11-15 03:14 | 3.14 | 1 | 3.8911 | 0.48639
2852 | 315626 | Basic Wall | A4 | A | Generic - 2" | Level 6 | 2" | Cube | No | 114.917 | 16.417 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 890.6223 | 2018-11-15 14:55 | 3.14 | 1 | 5.2283 | 0.65354
2853 | 315730 | Basic Wall | A5 | A | Generic - 2" | Level 6 | 2" | Cube | No | 65.334 | 9.25 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 501.8125 | 2018-11-16 06:36 | 3.14 | 1 | 2.9459 | 0.36823
2854 | 315781 | Basic Wall | A6 | A | Generic - 2" | Level 6 | 2" | Cube | No | 88.667 | 12.75 | 7 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 691.6875 | 2018-11-16 15:26 | 3.14 | 1 | 4.0605 | 0.50756
2855 | 315882 | Basic Wall | A7 | A | Generic - 2" | Level 6 | 2" | Cube | No | 41.125 | 8.085 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 438.6113 | 2018-11-17 03:37 | 3.14 | 1 | 2.5748 | 0.32186
2856 | 315913 | Basic Wall | A8 | A | Generic - 2" | Level 6 | 2" | Cube | No | 13.132 | 2.625 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 142.4062 | 2018-11-17 11:20 | 3.14 | 1 | 0.83599 | 0.1045
2857 | 315963 | Basic Wall | A9 | A | Generic - 2" | Level 6 | 2" | Cube | No | 23.681 | 4.583 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 248.6278 | 2018-11-17 13:51 | 3.14 | 1 | 1.4596 | 0.18244
2858 | 316077 | Basic Wall | A10 | A | Generic - 2" | Level 6 | 2" | Cube | No | 40.28 | 8.088 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 438.774 | 2018-11-17 18:14 | 3.14 | 1 | 2.5758 | 0.32197
2862 | 316454 | Basic Wall | A11 | A | Generic - 2" | Level 6 | 2" | Cube | No | 41.92 | 8.03 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 435.6275 | 2018-11-18 01:57 | 3.14 | 1 | 2.5573 | 0.31967
2863 | 316455 | Basic Wall | A12 | A | Generic - 2" | Level 6 | 2" | Cube | No | 7.468 | 1.529 | 5.2 | Jake's Cube Emporium | Joe's Construction Labor |  | 54.25 | 82.9483 | 2018-11-18 09:38 | 3.14 | 1 | 0.48694 | 0.060868
2861 | 316240 | Basic Wall | B1 | B | Generic - 5" | Level 6 | 5" | Interior | No | 365 | 36.5 | 10 | Jenny's Awesome Drywall | Jenny's Awesome Drywall |  | 76 | 2774 | 2018-11-12 | 0.75 | 3 | 48.6667 | 2.0278
2864 | 317715 | Basic Wall | B2 | B | Generic - 5" | Level 6 | 5" | Interior | No | 23.216 | 1.903 | 10 | Jenny's Awesome Drywall | Jenny's Awesome Drywall |  | 76 | 144.628 | 2018-11-14 00:40 | 0.75 | 3 | 2.5373 | 0.10572
2865 | 317775 | Basic Wall | B3 | B | Generic - 5" | Level 6 | 5" | Interior | No | 19.186 | 1.918 | 10 | Jenny's Awesome Drywall | Jenny's Awesome Drywall |  | 76 | 145.768 | 2018-11-14 03:12 | 0.75 | 3 | 2.5573 | 0.10656
2866 | 317837 | Basic Wall | B4 | B | Generic - 5" | Level 6 | 5" | Interior | No | 19.258 | 1.924 | 10 | Jenny's Awesome Drywall | Jenny's Awesome Drywall |  | 76 | 146.224 | 2018-11-14 05:46 | 0.75 | 3 | 2.5653 | 0.10689
2867 | 317871 | Basic Wall | B5 | B | Generic - 5" | Level 6 | 5" | Interior | No | 15.109 | 1.927 | 10 | Jenny's Awesome Drywall | Jenny's Awesome Drywall |  | 76 | 146.452 | 2018-11-14 08:20 | 0.75 | 3 | 2.5693 | 0.10706
Formulas:
PJC:Schedule = [PJC:Schedule, row above]+[PJC: Crew Days, row above]